## Product Catalog
Project Name | Agile Manifesto Project
StakeHolders/Customers/Users | abc/xyz/zxc etc.
Created By | Anubhav Ranjan
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
Create a web-based platform to educate and engage users about the Agile Manifesto and methodologies. | US001 | Create a Homepage for Agile Manifesto.. | As a user, I want to see a visually appealing homepage that introduces the Agile Manifesto so that I can quickly understand the purpose of the platform. | New | The homepage should include an introduction to Agile and its history. The homepage should have clear navigation to other sections of the platform. The design should be responsive and work on both desktop and mobile devices.
| US002 | Create Agile Values and Principles Page.. | As a user, I want to explore the core Agile values and principles interactively so that I can better understand and apply them in my projects. | New | A dedicated page should display the four Agile values. An interactive feature (e.g., click or hover) should explain the 12 principles of Agile. Each value and principle should include examples to help users relate to real-world scenarios.
| US003 | Resource Library Design | As a user, I want access to a library of Agile practices and templates so that I can download resources and implement Agile methodologies effectively. | New | The library should include resources for Scrum, Kanban, and other Agile practices. Users should be able to search and filter resources by category or keyword. Resources should be downloadable in common formats (e.g., PDF, Excel).
| US004 | Add Collaboration Features.. | As a registered user, I want to participate in discussions and comment on Agile resources so that I can share ideas and learn from others in the community. | New | Users should be able to register, log in, and authenticate themselves securely. A discussion forum should allow users to start threads and reply to existing ones. Users should be able to comment on resources and principles. Comments and forum discussions should have basic moderation features.

## Spring Planning
Project Name | Agile Manifesto Project
StakeHolders/Customers/Users | abc/xyz/zxc etc.
Created By | Anubhav Ranjan
Epic | User Story ID | Feature/Title | User Story | Story Points | Story Tasks | Story Tasks Points | Sprint | Sprint Details
Create a web-based platform to educate and engage users about the Agile Manifesto and methodologies. | US001 | Create a Homepage for Agile Manifesto.. | As a user, I want to see a visually appealing homepage that introduces the Agile Manifesto so that I can quickly understand the purpose of the platform. | 8 | 1.1: Design and implement a visually appealing homepage. | 4 | 1 | Complete the Homepage for Agile Manifesto.
[5 empty] | 1.2: Add an introduction to Agile and its history. | 2
[5 empty] | 1.3: Include navigation to other sections of the platform. | 2
| US002 | Create Agile Values and Principles Page.. | As a user, I want to explore the core Agile values and principles interactively so that I can better understand and apply them in my projects. | 5 | 2.1: Create a page to display the four core Agile values | 3 | 2 | Build the Agile Values and Principles section.
[5 empty] | 2.2: Implement an interactive feature to explain the 12 principles. | 1
[5 empty] | 2.3: Add examples to illustrate each value and principle. | 1
| US003 | Resource Library Design | As a user, I want access to a library of Agile practices and templates so that I can download resources and implement Agile methodologies effectively. | 4 | 3.1: Design a library for Agile practices (Scrum, Kanban, etc.). | 2 | 3 | Develop the Resource Library.
[5 empty] | 3.2: Include downloadable resources like templates and guides. | 1
[5 empty] | 3.3: Add search and filter functionality. | 1
| US004 | Add Collaboration Features.. | As a registered user, I want to participate in discussions and comment on Agile resources so that I can share ideas and learn from others in the community. | 8 | 4.1: Develop a discussion forum for users. | 4 | 4 | Implement Collaboration Features and perform final testing.
[5 empty] | 4.2: Enable users to comment on resources and principles. | 2
[5 empty] | 4.3: Implement user authentication for collaboration features. | 2

## Tasks
Story Task 1.1: SubTasks | Assignee | Status | Story Task 1.2: SubTasks | Assignee | Status | Story Task 1.3: SubTasks | Assignee | Status
Create wireframes and mockups for the homepage | Designer | Completed | Research and draft content about Agile and its origins | QA | Completed | Design a navigation menu with links to other sections | Designer | Completed
Develop HTML and CSS for the homepage layout. | Developer | Completed | Format and add content to the homepage. | Developer | Completed | Implement navigation menu functionality using JavaScript. | Developer | Ongoing
Implement responsive design for mobile and desktop. | Developer | Completed | Ensure the content is concise and visually appealing. | Developer | To-Do | Test navigation links for usability and accessibility | Tester | To-Do
Integrate animations for a polished user experience. | Developer | Ongoing
Conduct usability testing and gather feedback. | Tester | To-Do
Story Task 2.1: SubTasks |  |  | Story Task 2.2: SubTasks |  |  | Story Task 2.3: SubTasks
Design the layout for the Agile values page. | Designer | To-Do | Design the interactive element (e.g., accordion or hover tooltips). | Designer | To-Do | Research real-world examples for each value and principle. | QA | To-Do
Add descriptions for each of the four Agile values. | Developer | To-Do | Develop the interactive feature using JavaScript. | Developer | To-Do | Format and add examples to the respective sections. | Developer | To-Do
Ensure the page design is consistent with the homepage. | Designer | To-Do | Test the functionality across different browsers. | Tester | To-Do | Ensure examples are easy to understand and relevant. | QA | To-Do
Story Task 3.1: SubTasks |  |  | Story Task 3.2: SubTasks |  |  | Story Task 3.3: SubTasks
Create wireframes for the library layout. | Designer | To-Do | Gather and prepare downloadable Agile resources. | QA | To-Do | Design and implement a search bar. | Developer | To-Do
Develop the frontend for the resource library. | Developer | To-Do | Implement file download functionality. | Developer | To-Do | Develop filter options (e.g., by category, keyword). | Developer | To-Do
Add placeholders for Agile practice categories. | Developer | To-Do | Test download links and verify resource accessibility. | Tester | To-Do | Test search and filter functionality with sample data. | Tester | To-Do
Story Task 4.1: SubTasks |  |  | Story Task 4.2: SubTasks |  |  | Story Task 4.3: SubTasks
Design the forum layout and features. | Developer | To-Do | Design the comment input field and UI. | Designer | To-Do | Set up the authentication system (e.g., registration, login). | Developer | To-Do
Set up the database schema for forum threads and replies. | Developer | To-Do | Develop backend APIs for storing comments. | Developer | To-Do | Secure the API endpoints for authenticated users. | Developer | To-Do
Develop backend APIs for creating, reading, and replying to threads. | Developer | To-Do | Implement frontend integration with APIs. | Developer | To-Do | Test authentication and ensure user data security. | Tester | To-Do
Build the frontend for the forum and integrate with APIs. | Developer | To-Do | Test the comment functionality. | Tester | To-Do
Test forum functionality and fix issues. | Tester | To-Do